## in
Phase | Task | Status | Start Date | Target Date | Notes / Output
1 | AWS App Runner service deployed and accessible | Not Started
1 | CloudFront and S3 correctly configured for static content | Not Started
1 | Cognito authentication working (test login) | Not Started
1 | TLS certificate configured and valid | Not Started
1 | Documentation provided for deployment | Not Started
2 | Organisational data isolation implemented (org_id recognised) | Not Started
2 | Routing logic includes organisation-level handling | Not Started
2 | DynamoDB or similar configured for storing user/tenant data | Not Started
2 | Sample org/test users created | Not Started
2 | Documentation explains tenant config | Not Started
3 | FastAPI endpoints accessible via frontend | Not Started
3 | Chat endpoint responds to test message | Not Started
3 | LLM integration stubbed or functioning | Not Started
3 | Basic logging working for chat requests | Not Started
3 | RAG stub logic recognises organisation context | Not Started
4 | RAG returns tenant-specific data (manual ingestion OK) | Not Started
4 | Conversation memory persists and recalls messages | Not Started
4 | Prompt routing based on sample intents | Not Started
4 | LLM completions return formatted answers | Not Started
4 | Internal logging supports debugging flow | Not Started
5 | All features validated via walkthrough | Not Started
5 | Configuration and deployment documentation complete | Not Started
5 | GitHub repo and access confirmed | Not Started
5 | All required secrets/environment vars documented | Not Started
5 | Final invoice conditions met | Not Started